‘To Do’ List

This is an overview of the elements of Growing Leaders. Items in light green relate to a second course starting a year after the first. It is in Word so you can tailor it to your requirements. Please do send us your improved versions!

(Idea from Peter MacKenzie, running GL in Harrow)

| Date | What | Who | Done |
| --- | --- | --- | --- |
| Feb 2006 | Plan dates for course, including mentors meeting, book venues (home and away) |  |  |
| Mar-May 2006 | Pray about whom to invite. Discuss with others. |  |  |
| May 2006 | Send out personal invites for exploratory session. |  |  |
| June 2006 | Pray and prepare for Exploratory Session - Catering - Handouts - Material (check website for updates) |  |  |
| Late June 2006 | Exploratory Session |  |  |
| July-Aug 2006 | Plan date for mentors meeting |  |  |
|  | Order and purchase enough Growing Leaders books for each participant and each mentor (unless they already have one), using discount card in pack for purchases from CPAS. |  |  |
|  | Pray and recruit mentors, invite to mentors’ meeting |  |  |
|  | Recruit set-up and refreshments helpers, mentor coordinator?, prayer coordinator |  |  |
|  | Pray and prepare for mentors’ meeting: - PowerPoint presentation and handout - Growing Leaders Mentor Guide - Mentoring review sheets |  |  |
|  | Send out first assignment, with letter of welcome, and Growing Leaders book |  |  |
| Early Sept 2006 | Mentors preparation meeting |  |  |
| Sept 2006 | Pray and prepare for session 1 - Folders with covers and names - Training materials - Handouts - Other resources from list - Refreshments and extras |  |  |
|  | GL Session 1 |  |  |
|  | Evaluate session 1; e-mail mentors |  |  |
| Oct 2006 | Pray and prepare for session 2 - Training materials - Handouts - Other resources from list |  |  |
|  | GL Session 2 |  |  |
|  | Evaluate session 2; e-mail mentors |  |  |
| Nov 2006 | Pray and prepare for session 3 - Training materials - Handouts - Other resources from list |  |  |
|  | GL Session 3 |  |  |
|  | Evaluate session 3; e-mail mentors |  |  |
| Dec 2006 | Pray and prepare for session 4 - Training materials - Handouts - Other resources from list |  |  |
|  | GL Session 4 |  |  |
|  | Evaluate session; e-mail mentors |  |  |
| Jan 2007 | Pray and prepare for session 5 - Training materials - Handouts - Other resources from list |  |  |
|  | GL Session 5 |  |  |
|  | Evaluate session 5; e-mail mentors |  |  |
| Feb 2007 | Pray and prepare for session 6 - Training materials - Handouts - Other resources from list |  |  |
|  | GL Session 6 |  |  |
|  | Evaluate session; e-mail mentors |  |  |
|  | Plan dates for next course, including mentors meeting, book venues (home and away) |  |  |
| Mar 2007 | Pray and prepare for session 7; (1. Handouts 2. Other resources from list) |  |  |
|  | GL Session 7 |  |  |
|  | Evaluate session; e-mail mentors |  |  |
| Mar-May 2007 | Pray about whom to invite to the next course. Discuss with others. |  |  |
| Apr 2007 | Pray and prepare for session 8; - Training materials - Handouts - Other resources from list |  |  |
|  | GL Session 8 |  |  |
|  | Evaluate session; e-mail mentors |  |  |
| May 2007 | Pray and prepare for session - Training materials - Handouts - Other resources from list |  |  |
|  | GL Session 9 |  |  |
|  | Evaluate session; e-mail mentors |  |  |
|  | Send out personal invites for Exploratory Session for next Growing Leaders course |  |  |
| Jun 2007 | Pray and prepare for session 10 - Training materials - Handouts - Other resources from list - Catering |  |  |
|  | GL Session 10 |  |  |
|  | Evaluate session; e-mail mentors |  |  |
| June 2007 | Pray and prepare for Exploratory Session for Growing Leaders B |  |  |
| Late June 2007 | Exploratory Session |  |  |
| July 2007 | Meet with GL participants and mentors for evaluation |  |  |
|  | Thank and give gift to all who helped on course including mentors |  |  |
|  | Deadline for answers. Start recruiting mentors. Send out first project. |  |  |